## Tabelle1
CREMLIN WP4 NEUTRON DELIVERABLES and MILESTONES due to CREMLIN GA 1602784, project start September, 1st 2015
|  | 1st YEAR: Sep. 2015-Aug. 2016 | [11 empty] | 2nd YEAR: Sep.2016-Aug.2017 | [11 empty] | 3rd YEAR: Sep.2017 - Aug.2018
CREMLIN; Connecting Russian and European Measures for Large-scale Research Infrastructure |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q5 |  |  | Q6 |  |  | Q7 |  |  | Q8 |  |  | Q9 |  |  | Q10 |  |  | Q11 |  |  | Q12
|  | IX | X | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | V | V I | VII | VIII
|  | Q1 IX: 2. NSAC; Q2 XII: 6; Q3 III: 3. NSAC; Q4 VI: 12 |  | 4.NSAC |  |  | 18 |  |  | 21 |  |  | 24 |  |  | 27 |  |  | 30 |  |  | 33 |  |  | 36
WP4. | Science Cooperation with the PIK reactor in the field of neutron sources | bar: Q2 II; Q3 V
Task 4.1, HZG | Mapping | Q3 III: HZG; Q3 V: D4.2(M9)
Workshop on mapping user demands (D4.2)
Workshop on Neutron Scattering Methods for Engineering Materials
Task 4.2, JÜLICH | Instrumentation Concept for PIK reactor | Q3 III: JÜLICH MS5(M9) | [21 empty] | JÜLICH |  |  | D4.3(M36)
PIK Subcommittees established (MS5)
Meetings of PIK Sub-Committees (referee to NSAC Sub-Com. Calender)
Guidelines PIK Instrument Concept (D4.3)
Task 4.3, PNPI | Education and Training Program | Q2 XII: PNPI; Q2 II: D4.1(M6)
Programme developed (D4.1)
School on Design Methods for Neutron Instrumentation
School on Modern Neutron Simulation Packages
Training Course on Simulation of Neutron Scattering Instruments
Task 4.4, ILL | Data Management | [33 empty] | ILL |  | D4.4(M36) | bar: Q2 II; Q3 V
Recommendation Standard Data Policy developed (D4.4) | bar: Q2 II; Q3 V
Task 4.5, TUM | User System | [33 empty] | TUM |  | D4.5(M36) | bar: Q2 II; Q3 V
Workshop on Advanced Sample Environment for Neutron Instrumentation | bar: Q2 II; Q3 V
Workshop on Engineering for Neutron Construction | bar: Q2 II; Q3 V
Recommendation on PIK User System (D4.5) | bar: Q2 II; Q3 V
LIST of DELIVERABLES and MILESTONES
D4.1/Feb 2016 | Development of the Education and Training
PNPI/report | Programme on Neutron Instrumentation
LIST of planned WORKSHOPS, MEETINGS and SCHOOLS due to committed ressources (Table3.4b)
D4.2/May,2016 | Workshop on mapping user demands | Q1 XI: Lead Beneficiary |  | ACTIVITY | [17 empty] | Ressources
HZG/workshop |  | Q1 X: 1.; Q1 XI: JÜLICH; Q4 VI: School on Design Methods for Neutron Instrumentation | [19 empty] | 8 | 000 EURO
|  | Q1 X: 2.; Q1 XI: JÜLICH; Q4 VI: School on Modern Neutron Simulation Packages | [19 empty] | 8 | 000 EURO
MS5/May,2016 | All Subcommittees for PIK Instrument | Q1 X: 3.; Q1 XI: JÜLICH; Q4 VI: Training Course on Simulation of Neutron Scattering Instruments | [19 empty] | 8 000 EURO
JÜLICH/impliment. | Concept established | Q1 X: 4.; Q1 XI: PNPI; Q4 VI: Meetings of Subcommittees on the PIK Instrument Concept | [19 empty] | 8 | 000 EURO
|  | Q1 X: 5.; Q1 XI: HZG; Q4 VI: Workshop on Neutron Scattering Methods for Engineering Materials | [19 empty] | 8 | 000 EURO
D4.3/Aug. 2018 | Guidelines for the general | Q4 VI: Science
JÜLICH/report | PIK Instrument Concept | Q1 X: 6.; Q1 XI: TUM; Q4 VI: Workshop on Engineering for Neutron Construction | [19 empty] | 7 | 000 EURO
|  | Q1 X: 7.; Q1 XI: TUM; Q4 VI: Workshop on Advanced Sample Environment for Neutron | [19 empty] | 8 | 000 EURO
D4.4/Aug.2018 | Recommendation on | Q4 VI: Instrumentation
ILL/report | Common Data Standard Policy
D4.5/Aug.2018 | Recommendation on the state-of-the-art
TUM / report | user system for PIK

## Kompatibilitätsbericht
Kompatibilitätsbericht für Kopie von WP4_Gantt-Chart Deliverables.xls
Ausführen auf 26.08.2014 19:10
Die folgenden Features in dieser Arbeitsmappe werden von früheren Excel-Versionen nicht unterstützt. Diese Features gehen beim Öffnen dieser Arbeitsmappe in einer früheren Excel-Version oder beim Speichern in einem früheren Dateiformat möglicherweise verloren oder werden beschädigt.
Geringer Genauigkeitsverlust | Anzahl | Version
Einige Zellen oder Formatvorlagen in dieser Arbeitsmappe enthalten eine Formatierung, die vom ausgewählten Dateiformat nicht unterstützt wird. Diese Formate werden in das ähnlichste verfügbare Format konvertiert. | 41 | Excel 97-2003